## Power 11 Build
RFx #: | BDA-CAB-IDT-IBMI-RFP-2026-08
Project Name: | IBMi Infrastructure Upgrade
Description | This template must capture the plan to deploy and configure the new IBM Power11 infrastructure in preparation for the migration from the existing Power10 environment
Prepared By:
Implementation Phase | Activity / Task | Duration (hrs) | Owner | Time Estimate | Remote / Onsite | Required Downtime | Notes
Project Planning and Preparation
Power11 Server Installation and Configuration
Hardware Management Console (HMC) Installation and Configuration
Keyboard, Video, and Mouse (KVM) Installation and Configuration
IBM Storage Virtualize (Storewize) SAN Installation and Configuration
Virtual I/O Server (VIOS) Installation and Configuration
Build and Configure Eight (8) IBM i Logical Partitions (LPARs)
Build and Configure Four (4) Red Hat Enterprise Linux (RHEL) Logical Partitions (LPARs)
Solution Validation, Testing, and Acceptance
Knowledge Transfer and Administrator Training
Project Documentation and Milestone Closeout

## Power 11 Migration
Basic Information
RFx #:
Project Name: | Power11, HMC, Switch, VIOS & FS5300 Migration
Project Description: | This template must capture the plan to migrate the existing IBM Power10 environment to the new IBM Power11 infrastructure.
Prepared By:
Implementation Phase | Activity / Task | Start Date | End Date | Owner | Time Estimate | Remote / Onsite | Required Downtime | Notes
Project Planning, Preparation and Readiness Assessment
Fibre Channel Switch Configuration and SAN Zoning
IBM Storage Virtualize (Storewize) SAN Migration
Migration of Seven (7) IBM i Logical Partitions (LPARs)
Migration of Seven (7) Red Hat Enterprise Linux (RHEL) Logical Partitions (LPARs)
Post-Migration Validation, Testing and Production Verification
Project Documentation and Milestone Closeout

## Power 10 Migration
Basic Information
RFx #:
Project Name: | Redeployment of Power10 as High Availability Target & Develpment Environments
Prepared By:
Implementation Phase | Activity / Task | Start Date | End Date | Owner | Time Estimate | Remote / Onsite | Required Downtime | Notes
Project Planning, Preparation and Readiness Assessment
Decommission, Relocate and Install IBM Power10 Server
Fibre Channel Switch Configuration, LPAR Connectivity and SAN Zoning
IBM Storage Virtualize (Storewize) SAN Configuration and Storage Migration
Migrate Seven (7) IBM i Logical Partitions (LPARs) from Power9 to Power10 and Build One (1) New IBM i LPAR
Build and Configure Four (4) Red Hat Enterprise Linux (RHEL) Logical Partitions (LPARs) on Power10
Data Domain Configuration and Storage Zoning
Configure SAN Replication Between the Power11 and Power10 Environments
Post-Migration Validation, Testing and Disaster Recovery Verification
Decommission Legacy IBM Power9 Infrastructure
Project Documentation and Closeout